## Sheet1
| Iteration | Story Points Completed | Total Completed | Forecast Completed | Forecast High | Forecast Low | MVP |  | Iteration | Story Points Completed | Total Completed | Forecast Completed | Forecast High | Forecast Low | MVP |  | Iteration | Story Points Completed | Total Completed | Forecast Completed | Forecast High | Forecast Low | MVP |  | Iteration | Story Points Completed | Total Completed | Forecast Completed | Forecast High | Forecast Low | MVP | Evalute for fixed time, variable scope |  | Iteration | Story Points Completed | Total Completed | Forecast Completed | Forecast High | Forecast Low | MVP |  | Iteration | Story Points Completed | Total Completed | Forecast Completed | Forecast High | Forecast Low | MVP
Historical | 1 | 9 | [5 empty] | Historical | 1 | 9 | 9 |  |  |  |  | Historical | 1 | 9 | 9 |  |  |  |  | Historical | 1 | 9 | 9 | [5 empty] | Historical | 1 | 9 | 9 |  |  |  | 250 | Historical | 1 | 9 | 9 |  |  |  | 250
| 2 | 18 | [6 empty] | 2 | 18 | 27 | [5 empty] | 2 | 18 | 27 | [5 empty] | 2 | 18 | 27 | [6 empty] | 2 | 18 | 27 |  |  |  | 250 |  | 2 | 18 | 27 |  |  |  | 250
| 3 | 25 | [6 empty] | 3 | 25 | 52 | [5 empty] | 3 | 25 | 52 | [5 empty] | 3 | 25 | 52 | [6 empty] | 3 | 25 | 52 |  |  |  | 300 |  | 3 | 25 | 52 |  |  |  | 300
| 4 | 15 | [6 empty] | 4 | 15 | 67 | [5 empty] | 4 | 15 | 67 | [5 empty] | 4 | 15 | 67 | [6 empty] | 4 | 15 | 67 |  |  |  | 300 |  | 4 | 15 | 67 |  |  |  | 300
| 5 | 30 | [6 empty] | 5 | 30 | 97 | [5 empty] | 5 | 30 | 97 | [5 empty] | 5 | 30 | 97 | [6 empty] | 5 | 30 | 97 |  |  |  | 225 |  | 5 | 30 | 97 |  |  |  | 225
| (Today) 6 | 21 | [6 empty] | (Today) 6 | 21 | 118 | [5 empty] | (Today) 6 | 21 | 118 | 118 |  |  |  |  | (Today) 6 | 21 | 118 | 118 | 118 | 118 |  |  |  | (Today) 6 | 21 | 118 | 118 | 118 | 118 | 225 |  | 6 | 21 | 118 |  |  |  | 225
Forecast | 7 | [6 empty] | Forecast | 7 | [6 empty] | Forecast | 7 |  |  | 140 |  |  |  | Forecast | 7 |  |  | 140 | 147.5498 | 132.4502 |  |  | Forecast | 7 |  |  | 140 | 147.5498 | 132.4502 | 225 |  | Today (7) | 25 | 143 | 143 | 143 | 143 | 225
| 8 | [7 empty] | 8 | [7 empty] | 8 |  |  | 162 |  |  |  |  | 8 |  |  | 162 | 177.0997 | 146.9003 |  |  |  | 8 |  |  | 162 | 177.0997 | 146.9003 | 225 | Forecast | 8 |  |  | 168.3333 | 172.8426 | 163.8241 | 225
| 9 | [7 empty] | 9 | [7 empty] | 9 |  |  | 184 |  |  |  |  | 9 |  |  | 184 | 206.6495 | 161.3505 |  |  |  | 9 |  |  | 184 | 206.6495 | 161.3505 | 225 |  | 9 |  |  | 193.6667 | 202.6852 | 184.6482 | 225
| 10 | [7 empty] | 10 | [7 empty] | 10 |  |  | 206 |  |  |  |  | 10 |  |  | 206 | 236.1993 | 175.8007 |  |  |  | 10 |  |  | 206 | 236.1993 | 175.8007 | 225 |  | 10 |  |  | 219 | 232.5277 | 205.4723 | 225
| 11 | [7 empty] | 11 | [7 empty] | 11 |  |  | 228 |  |  |  |  | 11 |  |  | 228 | 265.7492 | 190.2508 |  |  |  | 11 |  |  | 228 | 265.7492 | 190.2508 | 225 |  | 11 |  |  | 244.3333 | 262.3703 | 226.2963 | 225
| 12 | [7 empty] | 12 | [7 empty] | 12 |  |  | 250 |  |  |  |  | 12 |  |  | 250 | 295.299 | 204.701 |  |  |  | 12 |  |  | 250 | 295.299 | 204.701 | 225 |  | 12 |  |  | 269.6667 | 292.2129 | 247.1204 | 225
| 13 | [7 empty] | 13 | [7 empty] | 13 |  |  | 272 |  |  |  |  | 13 |  |  | 272 | 324.8488 | 219.1512 |  |  |  | 13 |  |  | 272 | 324.8488 | 219.1512 | 225 |  | 13 |  |  | 295 | 322.0555 | 267.9445 | 225
| 14 | [7 empty] | 14 | [7 empty] | 14 |  |  | 294 |  |  |  |  | 14 |  |  | 294 | 354.3987 | 233.6013 |  |  |  | 14 |  |  | 294 | 354.3987 | 233.6013 | 225 |  | 14 |  |  | 320.3333 | 351.8981 | 288.7686 | 225
| 15 | [7 empty] | 15 | [7 empty] | 15 |  |  | 316 |  |  |  |  | 15 |  |  | 316 | 383.9485 | 248.0515 |  |  |  | 15 |  |  | 316 | 383.9485 | 248.0515 | 225 |  | 15 |  |  | 345.6667 | 381.7407 | 309.5927 | 225
|  | Average Points Completed Last 3 Sprints: | [7 empty] | Average Points Completed Last 3 Sprints: | [7 empty] | Average Points Completed Last 3 Sprints: |  |  |  | 22 |  |  |  | Average Points Completed Last 3 Sprints: |  |  |  | 22 |  |  |  |  | Average Points Completed Last 3 Sprints: |  |  |  | 22 |  |  |  | Average Points Completed Last 3 Sprints: |  |  |  | 25.3333
|  | Standard Deviation Points Last 3 Sprints | [7 empty] | Standard Deviation Points Last 3 Sprints | [7 empty] | Standard Deviation Points Last 3 Sprints | [7 empty] | Standard Deviation Points Last 3 Sprints |  |  |  | 7.5498 |  |  |  |  | Standard Deviation Points Last 3 Sprints |  |  |  | 7.5498 |  |  |  | Standard Deviation Points Last 3 Sprints |  |  |  | 4.5092
Velocity over time | [7 empty] | Sum velocity over time and plot | [7 empty] | Add a forecast | [7 empty] | Add forecast highs and lows | [8 empty] | Evaluate for fixed scope, variable time (MVP) | [7 empty] | Update for Sprint 7